Context Foundry

MVP 2: Scale, Extract, Evaluate

Weeks 5-10 Implementation Plan

From Walking Skeleton to Production-Ready Architecture

# Executive Summary

Duration: 6 weeks (Weeks 5-10 from project start)

Prerequisite: MVP 1 walking skeleton validated—tri-memory architecture working, uncertainty surfacing confirmed, provenance tracking operational

Objective: Scale the validated architecture to meaningful data volume, introduce entity extraction from unstructured sources, and execute rigorous comparative evaluation against GraphRAG baseline

### Key Outcomes

- 10x data scale (from ~200 entities to 2,000+)

- Entity extraction pipeline operational (the hard part we deferred)

- GraphRAG baseline built and evaluated fairly

- 100-query blind evaluation completed

- Learning loop executed with real feedback

- Go/no-go decision on production investment

# Success Criteria

## Primary Metrics

| Metric | Target | Measurement |
| --- | --- | --- |
| Multi-hop accuracy | ≥10% better than GraphRAG | Blind evaluation, 100 queries |
| Entity extraction precision | ≥85% | Against human-validated sample |
| Entity extraction recall | ≥75% | Against human-validated sample |
| Confidence calibration | ±10% | Predicted vs actual by bucket |
| Uncertainty detection | ≥90% wrong answers flagged | Correlation analysis |
| Rule compliance | Zero violations | All outputs validated |
| Latency p95 | <5 seconds at 2,000 entities | End-to-end query |
| Learning loop improvement | Measurable adjustment | Before/after comparison |

## Secondary Metrics

| Metric | Target |
| --- | --- |
| Duplicate detection precision | ≥90% |
| Conflict detection rate | ≥80% of inserted contradictions caught |
| Human feedback capture | 100% of evaluation queries |
| STAGING → TRUSTED promotion rate | ≥70% of valid extractions |

## Anti-Metrics (Failure Indicators)

| Indicator | Threshold | Action |
| --- | --- | --- |
| Extraction precision <70% | Any sustained period | Stop and fix pipeline |
| GraphRAG wins on multi-hop | Statistically significant | Analyse why, document learnings |
| Calibration error >25% | Consistent | Confidence scoring broken |
| Latency p95 >10 seconds | At scale | Profile and optimise |

# Scope Definition

## In Scope (MVP 2)

### Data Scale

- 2,000+ entities

- 5,000+ relationships

- 100+ documents (runbooks, incident reports, architecture docs)

- 20+ symbolic rules

- Mix of synthetic and semi-structured real data (sanitised)

### Entity Extraction Pipeline

- NER for: Service, Component, Team, Person, Database, API

- Relation extraction for: DEPENDS_ON, OWNS, SUPPORTS, MEMBER_OF

- Confidence scoring on extractions

- Provenance linking to source sentence

- Duplicate detection and flagging

### Graph Lifecycle (Full)

- STAGING layer populated by extraction pipeline

- Gardener agent running on schedule (every 5 minutes)

- Promotion criteria enforced (confidence, corroboration, dwell time)

- Conflict detection and resolution

- Confidence decay on stale facts

- Demotion to ARCHIVED

### Identity Resolution

- Duplicate detection signals (name similarity, alias overlap, relationship overlap)

- Conservative merge policy (auto-merge >0.95, review 0.70-0.95)

- Merge audit trail

- No auto-merge for Person entities (human review required)

### Learning Loop (Operational)

- FeedbackRecord captured for every evaluation query

- Weekly learning cycle executed (minimum 2 cycles during MVP 2)

- Threshold adjustments based on calibration analysis

- Learning log maintained

### GraphRAG Baseline

- Same corpus, same LLM, same hardware

- Fair implementation (not a straw man)

- Same 100 queries

- Blind evaluation protocol

### Evaluation

- 100 queries (40 single-hop, 40 multi-hop, 10 adversarial, 10 ambiguous)

- Blind evaluation (anonymised responses)

- Minimum 2 evaluators per query

- Statistical analysis with significance testing

## Out of Scope (MVP 2)

| Excluded | Rationale | When |
| --- | --- | --- |
| Real-time streaming | Batch sufficient for evaluation | Phase 3 |
| Multi-tenant | Complexity | Phase 3 |
| Production security/auth | Evaluation environment only | Phase 3 |
| UI beyond demo | CLI and API sufficient | Phase 3 |
| OCR/image extraction | Text documents only | Phase 3 |
| Self-supervised learning | Human-in-the-loop sufficient | Phase 3 |
| High availability | Single node acceptable | Phase 3 |
| Kubernetes | Docker Compose sufficient | Phase 3 |

# Architecture Additions

## Entity Extraction Pipeline

The extraction pipeline is the core addition in MVP 2—this is the hard part we deliberately deferred from MVP 1.

### Pipeline Flow

RAW DOCUMENTS

│

▼

PERCEPTION LAYER

├── Document Ingestion (PDF/DOCX/MD/TXT)

├── Chunking (sentence-aware, 512 tokens max)

├── Entity Extraction (NER with schema-driven prompts)

├── Relation Extraction (RE with confidence scoring)

└── Extraction Validation (schema check, duplicate flag)

│

▼

STAGING LAYER

│

▼

GARDENER (promotion/demotion)

│

▼

TRUSTED LAYER

## Extraction Schema

### Entity Types

| Entity | Required Fields | Unique Key | Notes |
| --- | --- | --- | --- |
| Service | canonical_name | canonical_name |  |
| Component | canonical_name, component_type | canonical_name |  |
| Team | name | name |  |
| Person | canonical_name | email OR name | Human review required for merge |
| Database | canonical_name, db_type | canonical_name |  |
| Incident | external_id, title, severity | external_id |  |

### Relationship Types

| Type | Source | Target | Cardinality |
| --- | --- | --- | --- |
| DEPENDS_ON | Service, Component | Service, Component, Database | Many-to-many |
| OWNS | Team | Service, Component, Database | Many-to-one |
| SUPPORTS | Team | Service, Component | Many-to-many |
| MEMBER_OF | Person | Team | Many-to-many |
| AFFECTS | Incident | Service, Component, Database | Many-to-many |
| CAUSED_BY | Incident | Incident, Change | Many-to-one |

## Identity Resolution Signals

| Signal | Weight | Description |
| --- | --- | --- |
| exact_name_match | 0.95 | Canonical names identical |
| external_id_match | 0.95 | Same ID from authoritative source |
| email_match | 0.90 | Same email (Person entities) |
| alias_overlap | 0.40 | Shared alias between entities |
| name_similarity | 0.30 | Jaro-Winkler >0.85 |
| relationship_overlap | 0.25 | Same relationships to same targets |
| co_occurrence | 0.15 | Mentioned together frequently |

### Merge Policy

- Score ≥0.95: Auto-merge (except Person/Vendor)

- Score 0.70-0.95: Flag for human review

- Score <0.70: Treat as distinct entities

- Person entities: Always require human review for merge

## Gardener Agent (Full Specification)

The Gardener runs every 5 minutes and executes the following passes:

1. Decay Pass

- Query TRUSTED facts older than grace period

- Apply decay rate based on fact type:

• Ownership: 0.02/week, floor 0.5, grace 14 days

• Dependencies: 0.01/week, floor 0.6, grace 30 days

• Attributes: 0.015/week, floor 0.4, grace 7 days

- Flag facts below staleness threshold

2. Promotion Pass

Query STAGING facts meeting all criteria:

- confidence ≥ 0.75

- min_sources ≥ 2 OR 1 high-authority source (≥0.9)

- dwell_time ≥ 1 hour

- last_corroborated ≤ 30 days

- passes symbolic validation

- no unresolved conflicts with TRUSTED

3. Conflict Resolution

| Conflict Type | Resolution Strategy |
| --- | --- |
| attribute_mismatch | higher_authority_wins |
| relationship_contradiction | higher_confidence_wins |
| cardinality_violation | rule_determined |
| temporal_overlap | newer_wins |
| existence_conflict | human_required |

If margin <0.15: escalate to human review

4. Demotion Pass

- Query TRUSTED facts below demotion threshold (confidence <0.4)

- Query TRUSTED facts superseded by promoted facts

- Move to ARCHIVED with valid_to = now()

5. Cleanup Pass

- Prune STAGING facts older than 30 days

- Prune resolved conflicts older than 90 days

## Learning Loop (Full Specification)

Weekly learning cycle processes all unprocessed feedback records:

1. Aggregate

- Count by judgment: correct/incorrect/partial

- Group by error_type

- Group by entities_involved

2. Calibrate

Bucket responses by confidence:

- very_low: 0.0 - 0.3

- low: 0.3 - 0.5

- medium: 0.5 - 0.7

- high: 0.7 - 0.9

- very_high: 0.9 - 1.0

For each bucket, compare predicted accuracy to actual accuracy. Flag if error >15%.

3. Identify Patterns

- Queries with >2 incorrect responses → investigation queue

- Entity types with error_rate >0.3 → data quality flag

- Rules with missed_violations >0 → rule refinement queue

4. Adjust Thresholds

- If high-confidence bucket has low accuracy: confidence_threshold += 0.05

- If low-confidence bucket has high accuracy: confidence_threshold -= 0.05

5. Generate Report

Document cycle_date, accuracy_by_type, calibration_errors, threshold_adjustments, patterns_identified, action_items

6. Mark Processed

Update feedback_records.processed = TRUE with learning_action summary

# Evaluation Protocol

## Query Set Design

TOTAL: 100 queries

SINGLE-HOP (40 queries)

├── 15 entity lookup ("What team owns X?")

├── 15 relationship lookup ("What does X depend on?")

└── 10 attribute lookup ("What is the criticality of X?")

MULTI-HOP (40 queries)

├── 15 dependency chain ("If X fails, what is affected?")

├── 15 escalation path ("Who should be paged for SEV1 on X?")

└── 10 causal reasoning ("What caused incident Y?")

ADVERSARIAL (10 queries)

├── 4 missing data (answer doesn't exist)

├── 3 contradictory sources (conflicting info planted)

└── 3 ambiguous entities (similar names)

AMBIGUOUS (10 queries)

├── 5 underspecified ("Tell me about the database")

└── 5 temporal ambiguity ("Who owns the service?")

### Query Design Process

- Core team designs 50 queries (single-hop + multi-hop)

- Baseline Lead designs 30 queries (adversarial + half of multi-hop)

- External reviewer designs 20 queries (blind to architecture)

## Blind Evaluation Protocol

Phase 1: Execution

- Run all 100 queries on Context Foundry

- Run all 100 queries on GraphRAG baseline

- Same LLM, same hardware, same data

Phase 2: Anonymisation

- Strip system identifiers from responses

- Assign random labels (System A / System B)

- Randomise presentation order per evaluator

Phase 3: Evaluation

For each response, evaluator rates:

- Correctness: 0 (wrong), 0.5 (partial), 1 (correct)

- Completeness: 0-1 (answered all parts?)

- Explainability: 0-1 (can verify the answer?)

- Confidence appropriateness: 0-1 (was confidence level right?)

- Usefulness: 0-1 (would this help a human?)

Phase 4: Reconciliation

- Minimum 2 evaluators per query

- If evaluators disagree by >0.5 on correctness: third evaluator

Phase 5: Unblinding

- Reveal which system was which

- Statistical analysis (t-test, confidence intervals)

- Error pattern analysis

## Statistical Requirements

- Sample size: 100 queries

- Significance threshold: p < 0.05

- Paired t-test for accuracy comparison

- 95% confidence intervals for all metrics

- Effect size (Cohen's d) for accuracy difference

# Timeline

## Week 5: Data Scaling + Extraction Pipeline

| Day | Deliverable | Owner |
| --- | --- | --- |
| 1 | Scale synthetic data to 1,000 entities | Data |
| 2 | Document ingestion pipeline (PDF/DOCX/MD) | Backend |
| 3 | Entity extraction prompts + validation | ML |
| 4 | Relation extraction prompts + validation | ML |
| 5 | Extraction → STAGING integration | Backend |
| 6 | Human validation of extraction sample (10%) | All |
| 7 | Fix extraction issues, iterate on prompts | ML |

Week 5 Exit Criteria

☐ 1,000+ entities in graph (mix of loaded + extracted)

☐ Extraction precision ≥80% on validation sample

☐ Provenance tracks back to source sentence

## Week 6: Gardener + Identity Resolution

| Day | Deliverable | Owner |
| --- | --- | --- |
| 1 | Gardener scheduled execution (5-min cycle) | Backend |
| 2 | Confidence decay implementation | Backend |
| 3 | Conflict detection + resolution strategies | Backend |
| 4 | Identity Resolution: duplicate detection | ML |
| 5 | Identity Resolution: merge execution + audit | Backend |
| 6 | Human review queue for ambiguous merges | Backend |
| 7 | Integration testing: full lifecycle | All |

Week 6 Exit Criteria

☐ Gardener running on schedule

☐ STAGING facts promoting to TRUSTED

☐ Duplicates detected and flagged

☐ Conflicts logged and resolved (or escalated)

## Week 7: GraphRAG Baseline + Query Design

| Day | Deliverable | Owner |
| --- | --- | --- |
| 1 | GraphRAG implementation on same Postgres data | Baseline Lead |
| 2 | GraphRAG using same LLM | Baseline Lead |
| 3 | Verify GraphRAG answers basic queries | Baseline Lead |
| 4 | Design single-hop + multi-hop queries (50) | Core team |
| 5 | Design adversarial + ambiguous queries (30) | Baseline Lead |
| 6 | External reviewer designs blind queries (20) | External |
| 7 | Query set finalised, test harness built | All |

Week 7 Exit Criteria

☐ GraphRAG baseline functional

☐ 100 queries documented with expected answers

☐ Test harness runs queries on both systems

## Week 8: Scale to Full + Learning Loop

| Day | Deliverable | Owner |
| --- | --- | --- |
| 1 | Scale to 2,000 entities, 5,000 relationships | Data |
| 2 | Verify both systems handle scale | All |
| 3 | Run subset of queries, capture feedback | All |
| 4 | Execute first learning cycle | Backend |
| 5 | Analyse calibration, adjust thresholds | ML |
| 6 | Second learning cycle | Backend |
| 7 | Document learning loop outcomes | All |

Week 8 Exit Criteria

☐ 2,000+ entities in TRUSTED

☐ Both systems answering at scale

☐ 2 learning cycles completed

☐ Threshold adjustments documented

## Week 9: Full Evaluation

| Day | Deliverable | Owner |
| --- | --- | --- |
| 1 | Run all 100 queries on both systems | All |
| 2 | Anonymise responses | Integration |
| 3-5 | Blind evaluation (2+ evaluators) | External |
| 6 | Reconcile evaluator disagreements | All |
| 7 | Unblind, preliminary analysis | All |

Week 9 Exit Criteria

☐ All 100 queries evaluated

☐ Inter-evaluator agreement >80%

☐ Raw scores documented

## Week 10: Analysis + Decision

| Day | Deliverable | Owner |
| --- | --- | --- |
| 1 | Statistical analysis | ML |
| 2 | Error pattern analysis | All |
| 3 | Calibration analysis | ML |
| 4 | Write evaluation report | All |
| 5 | Prepare decision recommendation | Lead |
| 6 | Stakeholder presentation | All |
| 7 | Decision point: Proceed / Pivot / Stop | Stakeholder |

Week 10 Exit Criteria

☐ Evaluation report complete

☐ Statistical significance assessed

☐ Go/no-go decision documented

# Team Structure

## Core Team

| Role | Focus in MVP 2 |
| --- | --- |
| Backend Lead | Gardener, Identity Resolution, lifecycle management |
| ML Lead | Extraction pipeline, confidence calibration, learning loop |
| Baseline Lead | GraphRAG implementation, adversarial query design |
| Integration Lead | Test harness, evaluation infrastructure, documentation |

## Additional Support

| Role | Allocation | Responsibilities |
| --- | --- | --- |
| External Evaluators | Week 9 | Blind evaluation |
| Data Annotator | 50% Weeks 5-6 | Human validation of extractions |
| DevOps | 20% | Performance monitoring, scaling |

# Risk Register

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Extraction quality too low | High | High | Iterate prompts; narrow schema; increase validation |
| GraphRAG baseline too strong | Medium | High | Focus on uncertainty, provenance, rules |
| Scale causes latency issues | Medium | Medium | Profile early; optimise hot paths |
| Evaluator bias | Medium | High | Blind protocol; external evaluators |
| Identity Resolution errors | Medium | Medium | Conservative merge; human review for Person |
| Learning loop doesn't converge | Low | Medium | 2 cycles minimum; manual adjustment OK |
| Data quality varies by source | High | Medium | Track confidence by source; adjust trust |

# Decision Criteria (Week 10)

## Proceed to Phase 3 (Production Hardening) if:

☐ Multi-hop accuracy ≥10% better than GraphRAG (p < 0.05)

☐ Extraction precision ≥85%

☐ Confidence calibration within ±10%

☐ Zero rule violations in evaluation

☐ Learning loop showed measurable improvement

☐ Latency p95 <5 seconds at scale

☐ Team believes architecture scales

## Pivot if:

- GraphRAG wins on accuracy but CF wins on explainability/governance

- Extraction quality requires different approach (e.g., fine-tuned model)

- Latency requires architectural changes

- Specific query types fail systematically

## Stop if:

- GraphRAG wins on all metrics

- Extraction quality fundamentally broken (<70% precision)

- Architecture doesn't scale (latency >15 seconds)

- Team capacity insufficient for Phase 3

# Deliverables Checklist

## Code

☐ Entity extraction pipeline

☐ Relation extraction pipeline

☐ Gardener agent (full lifecycle)

☐ Identity Resolution agent

☐ Learning loop processor

☐ GraphRAG baseline implementation

☐ Evaluation test harness

☐ All code in version control

## Data

☐ 2,000+ entities in TRUSTED

☐ 5,000+ relationships

☐ 100+ documents ingested

☐ 20+ symbolic rules

☐ 100 evaluation queries with expected answers

☐ Feedback records for all evaluation queries

## Documentation

☐ Extraction schema specification

☐ Gardener configuration

☐ Identity Resolution policy

☐ Learning loop report (2 cycles)

☐ Evaluation protocol

☐ Evaluation report with statistics

☐ Decision recommendation

## Analysis

☐ Accuracy comparison (CF vs GraphRAG)

☐ Breakdown by query type

☐ Calibration curves

☐ Error pattern analysis

☐ Learning loop effectiveness

☐ Statistical significance tests

# Appendix: Extraction Quality Validation

## Human Validation Protocol

Sample 10% of extracted entities and relationships (random).

For each extraction, annotator assesses:

- Correctness: Is this actually in the source text?

- Completeness: Did extraction capture all properties?

- Boundary: Is the source span correctly identified?

- Type: Is the entity/relationship type correct?

### Metrics

- Precision = correct extractions / total extractions

- Recall = correct extractions / total entities in source

- Span accuracy = correct boundaries / total extractions

- Type accuracy = correct types / total extractions

### Thresholds

- Precision ≥85%: Proceed

- Precision 70-85%: Iterate on prompts, re-validate

- Precision <70%: Stop and redesign extraction approach

## Extraction Error Taxonomy

| Error Type | Description | Mitigation |
| --- | --- | --- |
| Hallucination | Entity not in source text | Stricter prompts; lower temperature |
| Missed entity | Entity in text but not extracted | Few-shot examples |
| Wrong type | Service classified as Component | Type definitions in prompt |
| Wrong boundary | Span includes extra text | Explicit span instructions |
| Merged entities | Two entities combined into one | Entity separation examples |
| Split entity | One entity split into two | Alias handling instructions |
| Wrong relationship | OWNS instead of SUPPORTS | Relationship definitions |
| Invented relationship | Relationship not stated | "Only extract explicit" instruction |

— End of Document —